## Defect Bug Report
Actual Result | Expected | Bug Owner | Priority | Severity | Spirint | Root Cause | Defect Type | Defect Creation date | Defect solved date
In Mini Statement its not allowing to view last 5 transaction details after all the details are filled and submit button is clicked | In Mini Statement it should allow to view last 5 transaction details after all the details are filled and submit button is clicked | Vanshika Joukani | High | High | 24 | Incorrect Implementation | Functional | 2021-02-23
In Customized Module, its not displaying transaction details after all the details are filled and submit button is clicked | In Customized Module, it should display transaction details after all the details are filled and submit button is clicked | Vanshika Joukani | High | High | 31 | Incorrect Implementation | Functional | 2021-02-23
In New Customer module its not allowing to add new customer after entering all the valid details and clicking on submit button | In New Customer module it should allow to add new customer after entering all the valid details and clicking on submit button | Vanshika Joukani | High | HIgh | 35 | Incorrect Implementation | Functional | 2021-02-23
In DOB,if we are entering today's date or future date,its allowing to add | In DOB,if we are entering today's date or future date,its should not allow to add | Vanshika Joukani | High | Low | 32 | Logic Error | Functional | 2021-02-23
In Edit Customer module, its not allowing to update all the fields | In Edit Customer module, it should allow to update all the fields | Vanshika Joukani | HIgh | High | 35 | Incorrect Implementation | Functional | 2021-02-23
In Delete Customer module, after entering all valid details its not allowing to delete customer | In Delete Customer module, after entering all valid details it should allow to delete customer | Vanshika Joukani | High | High | 32 | Incorrect Implementation | Functional | 2021-02-23
In New Account module its not allowing to create new account after entering all the valid details and clicking on submit button | In New Account module it should allow to create new account after entering all the valid details and clicking on submit button | Vanshika Joukani | HIgh | HIgh | 35 | Incorrect Implementation | Functional | 2021-02-23
In Edit Account module, its not allowing to update all the fields | In Edit Account module, it should allow to update all the fields | Vanshika Joukani | High | High | 31 | Incorrect Implementation | Functional | 2021-02-23
In Delete Account module, after entering all valid details its not allowing to delete account | In Delete Account module, after entering all valid details it should allow to delete account | Vanshika Joukani | High | High | 32 | Incorrect Implementation | Functional | 2021-02-23